## Summary Report
KAMPONG SPEU SUGAR CO., LTD.
Estimated Sugar Production Summary — Crushing Season 2026–2027
Source: Daily Production Plan RW'2627 (2.3M Tons) Rev.1, corrected
1. Crushing Season Overview
Item | Value | Remark
Start of crushing | 2026-12-01
End of crushing | 2027-04-16
Season length | 137 | ≈ 4.5 months
Finish of remelt sugar processing | 2027-09-02
2. Cane Crushing and Raw Sugar Production
Item | Quantity (Ton) | Remark
Total cane crushed | 2300000
Total raw sugar produced | 253000 | Yield 11.00%
3. Raw Sugar Allocation and Warehouse Capacity
Allocation / Storage | Quantity (Ton) | Remark
Raw sugar direct to white & refined processing | 124950 | 49.4% of raw sugar
Raw sugar to warehouse | 128050 | 50.6% of raw sugar
Total raw sugar | 253000 | 100%
Raw Sugar Warehouse 1 capacity | 45000
Raw Sugar Warehouse 2 capacity | 65000
Total raw sugar warehouse capacity | 110000
Packing raw sugar to jumbo bags (1.10 t) | 300 | Stored in Warehouse 2 (jumbo)
Packing period | 69 | 21-Jan-2027 to 30-Mar-2027
Total raw sugar packed to jumbo bags | 20700
Raw sugar in warhouse (10-Apr-2027) | 109720 | Within capacity — spare 280 t
4. Finished Goods Production (Full Campaign)
Product | Quantity (Ton) | Remark
Refined sugar | 106700 | 53,100 crushing season + 53,600 remelt seasion — 400 Ton/Day
White sugar | 133400 | 65,900 crushing season + 67,500 remelt seasion — 500 Ton/Day
Super Refined sugar | 2000 | Remelt period
Total finished goods | 242100 | 119,000 t season + 123,100 t remelt
5. Quota Sales, Remaining Stock and Finished Warehouse
Item | Quantity / Date | Remark
Quota sales rate | 500 | 05-Dec-2026 to 02-Sep-2027
Selling days | 272
Total quota sales | 136000 | 66,500 crusing season + 69,500 remelt seasion period
Remaining finished sugar (02-Sep-2027) | 106100
Refined Sugar Warehouse 1 capacity | 22000
Refined Sugar Warehouse 3 capacity | 47000
Total finished sugar warehouse capacity | 69000 | W1 + W3
Excess stock over capacity (02-Sep-2027) | 37100 | Additional sales / storage required
Warehouse full (even with 500 t/day sales) | 2027-05-28 | Per planning sheet daily tracker
If no refined/white delivery, warehouse full by | 2027-02-20 | Per planning sheet daily tracker
6. Key Observations
1. Raw sugar storage: planned stock (128,050 t) exceeds the 110,000 t capacity; 20,700 t packed into 1.10 t jumbo bags at 300 t/day (21-Jan to 30-Mar-2027) keeps peak stock at 109,720 t, just within capacity. Purchase jumbo bags before January.
2. Finished goods storage is not sufficient: even with 500 t/day quota sales, refined/white stock exceeds the 69,000 t capacity from 28-May-2027, ending at about 106,100 t (≈ 37,100 t above capacity) on 02-Sep-2027.
3. If no refined and white sugar is delivered out at all, the refined/white warehouse will be full on 20-Feb-2027.
4. Sales pace: 136,000 t sold (500 t/day × 272 days) is about 56% of the 242,100 t produced. About 640 t/day keeps ending stock within capacity; about 890 t/day clears all production by 02-Sep-2027.
5. Yield assumption: 11.00% raw sugar recovery on 2.3 million tons of cane; variations change warehouse and bagging requirements proportionally.
Note: figures per corrected Daily Production Plan (ProductionPlan_2627_2.3mt Rev.1); dates for warehouse-full are read from the plan's daily stock tracker.
Prepared by: Hang Sovanna — Finance Manager
Date: 16 July 2026

## RW'2627(2.3mt)Rev1(re)
Kampong Speu Sugar Co., Ltd.
Daily Production Plan — Crushing Season 2026/27 (2.3M Tons), Rev.1
|  | Target = | 2300000 | Tons
[19 empty] | Conditoning Silo | [11 empty] | Factory 1
| Day | Date | CANE (ton) | [5 empty] | R 1.1t (ton) |  |  |  |  | W 1.1t (ton) |  |  | (1.1t)R+W total (ton) |  | Super R (ton) |  |  | R 50kg (ton) | [7 empty] | R 50kg (ton) | [6 empty] | W 50kg (ton) | [5 empty] | Factory 1 Total |  | R repack |  | W repack | Totlal R+R repack(Diff.) |  |  |  | Powdered/day (ton) | SR+R+W total (ton) | [5 empty] | Raw Sugar in SILO (ton) | [7 empty] | Remark | Raw Sugar in SILO (ton) |  |  |  |  | Refined & White Sugar in SILO (ton)
|  |  | Today (target) | Today Actual | Todate Actual | Todate (target) | Beginning Balnace | 1.1t target | 1.1t actual | Wilmar Ship out | Ending Balance | Beginning Balnace | 1.1t target | 1.1t actual | Wilmar Ship out | Ending Balance | target | actual | target | 1T actual | 1kg/pc actual | R 50kg target | R 50kg actual | Stock Con.Silo | Wilmar Ship Out | Jie Srey Ship Out | You Hour Ship Out | Ending Balance | Beginning Balnace | R 50kg target | R 50kg actual | Wilmar Ship Out | Jie Srey Ship Out | You Hour Ship Out | Ending Balance | Beginning Balnace | W 50kg target | W 50kg actual | Wilmar Ship Out | Jie Srey Ship Out | You Hour Ship Out | Ending Balance | Target | Actual | target | actual | actual | target | actual | Diff | To-Date |  | target | actual | Grand Total R+W (50kg) | Raw Sugar (50Kg)Sell | Raw Sugar direct to Remelt Actual | Raw Sugar SILO to Remelt (Input) Actual | Raw Sugar SILO to Remelt (Input) Target | Raw Sugar target | Raw Sugar to Remelt target | Raw Sugar Actual | Raw Sugar to Silo Actual | Raw Sugar to Silo target | Raw Sugar (Remain in Silo) target | Raw Sugar (Remain in silo) Actual | *The cleaning day is adjusted according to suitability and situation. | Date | Raw Sugar W1+W2 |  |  | 110000 | Date | W1+W3 (Refined Sugar) |  |  | 69000
|  | 2024-11-28 | [15 empty] | 0 | [27 empty] | 13.2 |  |  | 13.2
|  | 2024-11-29 | [43 empty] | 0 |  |  | 0
|  | 2024-11-30 | [43 empty] | 18.5 | 14.4 |  | 18.5
|  | 2024-12-01 | [43 empty] | 37.6 | 18.15 |  | 37.6
|  | 2024-12-02 | [43 empty] | 51 | 1.1 |  | 51
|  | 2024-12-03 | [43 empty] | 52.9 | 0 |  | 52.9
|  | 2024-12-04 | [43 empty] | 134.9 | 0 |  | 134.9
|  | 2024-12-05 | [43 empty] | 151.5 | 0 |  | 151.5
|  | 2024-12-06 | [43 empty] | 114.5 | 0 |  | 114.5
|  | 2024-12-07 | [42 empty] | 200 | 189.25 |  | 200 | 189.25 | -10.75 | 8913.95
|  | 2024-12-08 | [42 empty] | 200 | 206.9 |  | 200 | 206.9 | 6.9 | 9120.85
[66 empty] | 0 |  |  | Open QTY | Received | Packing 1Ton Bag | Ending |  | Open QTY | Produce QTY | Sale QTY | End QTY
| 1 | 2026-12-01 | 17000 |  | 0 | 17000 | [46 empty] | 0 | 0 | [5 empty] | 1870 | 0 |  |  |  |  | 0 | Start Crushing & Remelt crop 26/27 | 2026-12-01 | 0 | 1870 |  | 1870 | 2026-12-01 | 0 | 0 |  | 0
| 2 | 2026-12-02 | 17000 |  | 0 | 34000 | [46 empty] | 0 | 0 | 0 |  |  |  |  | 1870 | 0 |  |  |  |  | 0 |  | 2026-12-02 | 1870 | 1870 |  | 3740 | 2026-12-02 | 0 | 0 |  | 0
| 3 | 2026-12-03 | 19000 |  | 0 | 53000 | [46 empty] | 0 | 0 | 0 |  |  |  |  | 2090 | 0 |  |  |  |  | 0 |  | 2026-12-03 | 3740 | 2090 |  | 5830 | 2026-12-03 | 0 | 0 |  | 0
| 4 | 2026-12-04 | 19000 |  | 0 | 72000 | [46 empty] | 0 | 0 | 0 |  |  |  |  | 2090 | 0 |  |  |  |  | 0 |  | 2026-12-04 | 5830 | 2090 |  | 7920 | 2026-12-04 | 0 | 0 |  | 0
| 5 | 2026-12-05 | 19000 |  | 0 | 91000 | [15 empty] | 350 |  | 350 | [12 empty] | 350 | [15 empty] | 700 | 0 | 0 |  |  |  |  | 2090 | 735 |  |  |  |  | 0 |  | 2026-12-05 | 7920 | 1355 |  | 9275 | 2026-12-05 | 0 | 700 | -500 | 200
S | 6 | 2026-12-06 | 19000 |  | 0 | 110000 | [15 empty] | 350 |  | 700 | [12 empty] | 350 | [15 empty] | 700 | 0 | 0 |  |  |  |  | 2090 | 735 |  |  |  |  | 0 |  | 2026-12-06 | 9275 | 1355 |  | 10630 | 2026-12-06 | 200 | 700 | -500 | 400
| 7 | 2026-12-07 | 19000 |  | 0 | 129000 | [15 empty] | 400 |  | 1000 | [12 empty] | 400 | [15 empty] | 800 | 0 | 0 |  |  |  |  | 2090 | 840 |  |  |  |  | 0 |  | 2026-12-07 | 10630 | 1250 |  | 11880 | 2026-12-07 | 400 | 800 | -500 | 700
| 8 | 2026-12-08 | 19000 |  | 0 | 148000 | [15 empty] | 400 |  | 1200 | [12 empty] | 400 | [15 empty] | 800 | 0 | 0 |  |  |  |  | 2090 | 840 |  |  |  |  | 0 |  | 2026-12-08 | 11880 | 1250 |  | 13130 | 2026-12-08 | 700 | 800 | -500 | 1000
| 9 | 2026-12-09 | 19000 |  | 0 | 167000 | [15 empty] | 400 |  | 1600 | [12 empty] | 400 | [15 empty] | 800 | 0 | 0 |  |  |  |  | 2090 | 840 |  |  |  |  | 0 |  | 2026-12-09 | 13130 | 1250 |  | 14380 | 2026-12-09 | 1000 | 800 | -500 | 1300
| 10 | 2026-12-10 | 19000 |  | 0 | 186000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-10 | 14380 | 1145 |  | 15525 | 2026-12-10 | 1300 | 900 | -500 | 1700
| 11 | 2026-12-11 | 19000 |  | 0 | 205000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-11 | 15525 | 1145 |  | 16670 | 2026-12-11 | 1700 | 900 | -500 | 2100
| 12 | 2026-12-12 | 19000 |  | 0 | 224000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-12 | 16670 | 1145 |  | 17815 | 2026-12-12 | 2100 | 900 | -500 | 2500
S | 13 | 2026-12-13 | 19000 |  | 0 | 243000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-13 | 17815 | 1145 |  | 18960 | 2026-12-13 | 2500 | 900 | -500 | 2900
| 14 | 2026-12-14 | 19000 |  | 0 | 262000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-14 | 18960 | 1145 |  | 20105 | 2026-12-14 | 2900 | 900 | -500 | 3300
| 15 | 2026-12-15 | 19000 |  | 0 | 281000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-15 | 20105 | 1145 |  | 21250 | 2026-12-15 | 3300 | 900 | -500 | 3700
| 16 | 2026-12-16 | 19000 |  | 0 | 300000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-16 | 21250 | 1145 |  | 22395 | 2026-12-16 | 3700 | 900 | -500 | 4100
| 17 | 2026-12-17 | 19000 |  | 0 | 319000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-17 | 22395 | 1145 |  | 23540 | 2026-12-17 | 4100 | 900 | -500 | 4500
| 18 | 2026-12-18 | 19000 |  | 0 | 338000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-18 | 23540 | 1145 |  | 24685 | 2026-12-18 | 4500 | 900 | -500 | 4900
| 19 | 2026-12-19 | 19000 |  | 0 | 357000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-19 | 24685 | 1145 |  | 25830 | 2026-12-19 | 4900 | 900 | -500 | 5300
S | 20 | 2026-12-20 | 9000 |  | 0 | 366000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 990 | 945 |  |  |  |  | 0 | Cleaning Plan#1 | 2026-12-20 | 25830 | 45 |  | 25875 | 2026-12-20 | 5300 | 900 | -500 | 5700
| 21 | 2026-12-21 | 0 |  | 0 | 366000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 0 | 945 |  |  |  |  | 0 |  | 2026-12-21 | 25875 | -945 |  | 24930 | 2026-12-21 | 5700 | 900 | -500 | 6100
| 22 | 2026-12-22 | 19000 |  | 0 | 385000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-22 | 24930 | 1145 |  | 26075 | 2026-12-22 | 6100 | 900 | -500 | 6500
| 23 | 2026-12-23 | 19000 |  | 0 | 404000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-23 | 26075 | 1145 |  | 27220 | 2026-12-23 | 6500 | 900 | -500 | 6900
| 24 | 2026-12-24 | 19000 |  | 0 | 423000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-24 | 27220 | 1145 |  | 28365 | 2026-12-24 | 6900 | 900 | -500 | 7300
| 25 | 2026-12-25 | 19000 |  | 0 | 442000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-25 | 28365 | 1145 |  | 29510 | 2026-12-25 | 7300 | 900 | -500 | 7700
| 26 | 2026-12-26 | 19000 |  | 0 | 461000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-26 | 29510 | 1145 |  | 30655 | 2026-12-26 | 7700 | 900 | -500 | 8100
S | 27 | 2026-12-27 | 19000 |  | 0 | 480000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-27 | 30655 | 1145 |  | 31800 | 2026-12-27 | 8100 | 900 | -500 | 8500
| 28 | 2026-12-28 | 19000 |  | 0 | 499000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-28 | 31800 | 1145 |  | 32945 | 2026-12-28 | 8500 | 900 | -500 | 8900
| 29 | 2026-12-29 | 19000 |  | 0 | 518000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-29 | 32945 | 1145 |  | 34090 | 2026-12-29 | 8900 | 900 | -500 | 9300
| 30 | 2026-12-30 | 19000 |  | 0 | 537000 | [12 empty] | 0 |  |  | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-30 | 34090 | 1145 |  | 35235 | 2026-12-30 | 9300 | 900 | -500 | 9700
| 31 | 2026-12-31 | 19000 |  | 0 | 556000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2026-12-31 | 35235 | 1145 |  | 36380 | 2026-12-31 | 9700 | 900 | -500 | 10100
| 32 | 2027-01-01 | 19000 |  | 0 | 575000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-01 | 36380 | 1145 |  | 37525 | 2027-01-01 | 10100 | 900 | -500 | 10500
| 33 | 2027-01-02 | 19000 |  | 0 | 594000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-02 | 37525 | 1145 |  | 38670 | 2027-01-02 | 10500 | 900 | -500 | 10900
S | 34 | 2027-01-03 | 19000 |  | 0 | 613000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-03 | 38670 | 1145 |  | 39815 | 2027-01-03 | 10900 | 900 | -500 | 11300
| 35 | 2027-01-04 | 19000 |  | 0 | 632000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-04 | 39815 | 1145 |  | 40960 | 2027-01-04 | 11300 | 900 | -500 | 11700
| 36 | 2027-01-05 | 19000 |  | 0 | 651000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-05 | 40960 | 1145 |  | 42105 | 2027-01-05 | 11700 | 900 | -500 | 12100
| 37 | 2027-01-06 | 19000 |  | 0 | 670000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-06 | 42105 | 1145 |  | 43250 | 2027-01-06 | 12100 | 900 | -500 | 12500
| 38 | 2027-01-07 | 19000 |  | 0 | 689000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-07 | 43250 | 1145 |  | 44395 | 2027-01-07 | 12500 | 900 | -500 | 12900
| 39 | 2027-01-08 | 19000 |  | 0 | 708000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-08 | 44395 | 1145 |  | 45540 | 2027-01-08 | 12900 | 900 | -500 | 13300
| 40 | 2027-01-09 | 19000 |  | 0 | 727000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-09 | 45540 | 1145 |  | 46685 | 2027-01-09 | 13300 | 900 | -500 | 13700
S | 41 | 2027-01-10 | 9000 |  | 0 | 736000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 990 | 945 |  |  |  |  | 0 | Cleaning Plan#2 | 2027-01-10 | 46685 | 45 |  | 46730 | 2027-01-10 | 13700 | 900 | -500 | 14100
| 42 | 2027-01-11 | 0 |  | 0 | 736000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 0 | 945 |  |  |  |  | 0 |  | 2027-01-11 | 46730 | -945 |  | 45785 | 2027-01-11 | 14100 | 900 | -500 | 14500
| 43 | 2027-01-12 | 19000 |  | 0 | 755000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-12 | 45785 | 1145 |  | 46930 | 2027-01-12 | 14500 | 900 | -500 | 14900
| 44 | 2027-01-13 | 19000 |  | 0 | 774000 | [15 empty] | 400 |  | 1600 | [5 empty] | 0 | [6 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-13 | 46930 | 1145 |  | 48075 | 2027-01-13 | 14900 | 900 | -500 | 15300
| 45 | 2027-01-14 | 19000 |  | 0 | 793000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-14 | 48075 | 1145 |  | 49220 | 2027-01-14 | 15300 | 900 | -500 | 15700
| 46 | 2027-01-15 | 19000 |  | 0 | 812000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-15 | 49220 | 1145 |  | 50365 | 2027-01-15 | 15700 | 900 | -500 | 16100
| 47 | 2027-01-16 | 19000 |  | 0 | 831000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-16 | 50365 | 1145 |  | 51510 | 2027-01-16 | 16100 | 900 | -500 | 16500
S | 48 | 2027-01-17 | 19000 |  | 0 | 850000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-17 | 51510 | 1145 |  | 52655 | 2027-01-17 | 16500 | 900 | -500 | 16900
| 49 | 2027-01-18 | 19000 |  | 0 | 869000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-18 | 52655 | 1145 |  | 53800 | 2027-01-18 | 16900 | 900 | -500 | 17300
| 50 | 2027-01-19 | 19000 |  | 0 | 888000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-19 | 53800 | 1145 |  | 54945 | 2027-01-19 | 17300 | 900 | -500 | 17700
| 51 | 2027-01-20 | 19000 |  | 0 | 907000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-20 | 54945 | 1145 |  | 56090 | 2027-01-20 | 17700 | 900 | -500 | 18100
| 52 | 2027-01-21 | 19000 |  | 0 | 926000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-21 | 56090 | 1145 | -300 | 56935 | 2027-01-21 | 18100 | 900 | -500 | 18500
| 53 | 2027-01-22 | 19000 |  | 0 | 945000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-22 | 56935 | 1145 | -300 | 57780 | 2027-01-22 | 18500 | 900 | -500 | 18900
| 54 | 2027-01-23 | 19000 |  | 0 | 964000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-23 | 57780 | 1145 | -300 | 58625 | 2027-01-23 | 18900 | 900 | -500 | 19300
S | 55 | 2027-01-24 | 19000 |  | 0 | 983000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-24 | 58625 | 1145 | -300 | 59470 | 2027-01-24 | 19300 | 900 | -500 | 19700
| 56 | 2027-01-25 | 19000 |  | 0 | 1002000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-25 | 59470 | 1145 | -300 | 60315 | 2027-01-25 | 19700 | 900 | -500 | 20100
| 57 | 2027-01-26 | 19000 |  | 0 | 1021000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-26 | 60315 | 1145 | -300 | 61160 | 2027-01-26 | 20100 | 900 | -500 | 20500
| 58 | 2027-01-27 | 19000 |  | 0 | 1040000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-27 | 61160 | 1145 | -300 | 62005 | 2027-01-27 | 20500 | 900 | -500 | 20900
| 59 | 2027-01-28 | 19000 |  | 0 | 1059000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-28 | 62005 | 1145 | -300 | 62850 | 2027-01-28 | 20900 | 900 | -500 | 21300
| 60 | 2027-01-29 | 19000 |  | 0 | 1078000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-29 | 62850 | 1145 | -300 | 63695 | 2027-01-29 | 21300 | 900 | -500 | 21700
| 61 | 2027-01-30 | 19000 |  | 0 | 1097000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-01-30 | 63695 | 1145 | -300 | 64540 | 2027-01-30 | 21700 | 900 | -500 | 22100
S | 62 | 2027-01-31 | 9000 |  | 0 | 1106000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 990 | 945 |  |  |  |  | 0 | Cleaning Plan#3 | 2027-01-31 | 64540 | 45 | -300 | 64285 | 2027-01-31 | 22100 | 900 | -500 | 22500
| 63 | 2027-02-01 | 0 |  | 0 | 1106000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 0 | 945 |  |  |  |  | 0 |  | 2027-02-01 | 64285 | -945 | -300 | 63040 | 2027-02-01 | 22500 | 900 | -500 | 22900
| 64 | 2027-02-02 | 19000 |  | 0 | 1125000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-02 | 63040 | 1145 | -300 | 63885 | 2027-02-02 | 22900 | 900 | -500 | 23300
| 65 | 2027-02-03 | 19000 |  | 0 | 1144000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-03 | 63885 | 1145 | -300 | 64730 | 2027-02-03 | 23300 | 900 | -500 | 23700
| 66 | 2027-02-04 | 19000 |  | 0 | 1163000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-04 | 64730 | 1145 | -300 | 65575 | 2027-02-04 | 23700 | 900 | -500 | 24100
| 67 | 2027-02-05 | 19000 |  | 0 | 1182000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-05 | 65575 | 1145 | -300 | 66420 | 2027-02-05 | 24100 | 900 | -500 | 24500
| 68 | 2027-02-06 | 19000 |  | 0 | 1201000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-06 | 66420 | 1145 | -300 | 67265 | 2027-02-06 | 24500 | 900 | -500 | 24900
S | 69 | 2027-02-07 | 19000 |  | 0 | 1220000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-07 | 67265 | 1145 | -300 | 68110 | 2027-02-07 | 24900 | 900 | -500 | 25300
| 70 | 2027-02-08 | 19000 |  | 0 | 1239000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-08 | 68110 | 1145 | -300 | 68955 | 2027-02-08 | 25300 | 900 | -500 | 25700
| 71 | 2027-02-09 | 19000 |  | 0 | 1258000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-09 | 68955 | 1145 | -300 | 69800 | 2027-02-09 | 25700 | 900 | -500 | 26100
| 72 | 2027-02-10 | 19000 |  | 0 | 1277000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-10 | 69800 | 1145 | -300 | 70645 | 2027-02-10 | 26100 | 900 | -500 | 26500
| 73 | 2027-02-11 | 19000 |  | 0 | 1296000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-11 | 70645 | 1145 | -300 | 71490 | 2027-02-11 | 26500 | 900 | -500 | 26900
| 74 | 2027-02-12 | 19000 |  | 0 | 1315000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-12 | 71490 | 1145 | -300 | 72335 | 2027-02-12 | 26900 | 900 | -500 | 27300
| 75 | 2027-02-13 | 19000 |  | 0 | 1334000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-13 | 72335 | 1145 | -300 | 73180 | 2027-02-13 | 27300 | 900 | -500 | 27700
S | 76 | 2027-02-14 | 19000 |  | 0 | 1353000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-14 | 73180 | 1145 | -300 | 74025 | 2027-02-14 | 27700 | 900 | -500 | 28100
| 77 | 2027-02-15 | 19000 |  | 0 | 1372000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-15 | 74025 | 1145 | -300 | 74870 | 2027-02-15 | 28100 | 900 | -500 | 28500
| 78 | 2027-02-16 | 19000 |  | 0 | 1391000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-16 | 74870 | 1145 | -300 | 75715 | 2027-02-16 | 28500 | 900 | -500 | 28900
| 79 | 2027-02-17 | 19000 |  | 0 | 1410000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-17 | 75715 | 1145 | -300 | 76560 | 2027-02-17 | 28900 | 900 | -500 | 29300
| 80 | 2027-02-18 | 19000 |  | 0 | 1429000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-18 | 76560 | 1145 | -300 | 77405 | 2027-02-18 | 29300 | 900 | -500 | 29700
| 81 | 2027-02-19 | 19000 |  | 0 | 1448000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-19 | 77405 | 1145 | -300 | 78250 | 2027-02-19 | 29700 | 900 | -500 | 30100
| 82 | 2027-02-20 | 19000 |  | 0 | 1467000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-20 | 78250 | 1145 | -300 | 79095 | 2027-02-20 | 30100 | 900 | -500 | 30500
S | 83 | 2027-02-21 | 9000 |  | 0 | 1476000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 990 | 945 |  |  |  |  | 0 | Cleaning Plan#4 | 2027-02-21 | 79095 | 45 | -300 | 78840 | 2027-02-21 | 30500 | 900 | -500 | 30900
| 84 | 2027-02-22 | 0 |  | 0 | 1476000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 0 | 945 |  |  |  |  | 0 |  | 2027-02-22 | 78840 | -945 | -300 | 77595 | 2027-02-22 | 30900 | 900 | -500 | 31300
| 85 | 2027-02-23 | 19000 |  | 0 | 1495000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-23 | 77595 | 1145 | -300 | 78440 | 2027-02-23 | 31300 | 900 | -500 | 31700
| 86 | 2027-02-24 | 19000 |  | 0 | 1514000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-24 | 78440 | 1145 | -300 | 79285 | 2027-02-24 | 31700 | 900 | -500 | 32100
| 87 | 2027-02-25 | 19000 |  | 0 | 1533000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-25 | 79285 | 1145 | -300 | 80130 | 2027-02-25 | 32100 | 900 | -500 | 32500
| 88 | 2027-02-26 | 19000 |  | 0 | 1552000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-26 | 80130 | 1145 | -300 | 80975 | 2027-02-26 | 32500 | 900 | -500 | 32900
| 89 | 2027-02-27 | 19000 |  | 0 | 1571000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-27 | 80975 | 1145 | -300 | 81820 | 2027-02-27 | 32900 | 900 | -500 | 33300
S | 90 | 2027-02-28 | 19000 |  | 0 | 1590000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-02-28 | 81820 | 1145 | -300 | 82665 | 2027-02-28 | 33300 | 900 | -500 | 33700
| 91 | 2027-03-01 | 19000 |  | 0 | 1609000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-01 | 82665 | 1145 | -300 | 83510 | 2027-03-01 | 33700 | 900 | -500 | 34100
| 92 | 2027-03-02 | 19000 |  |  | 1628000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-02 | 83510 | 1145 | -300 | 84355 | 2027-03-02 | 34100 | 900 | -500 | 34500
| 93 | 2027-03-03 | 19000 |  |  | 1647000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-03 | 84355 | 1145 | -300 | 85200 | 2027-03-03 | 34500 | 900 | -500 | 34900
| 94 | 2027-03-04 | 19000 |  |  | 1666000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-04 | 85200 | 1145 | -300 | 86045 | 2027-03-04 | 34900 | 900 | -500 | 35300
| 95 | 2027-03-05 | 19000 |  |  | 1685000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-05 | 86045 | 1145 | -300 | 86890 | 2027-03-05 | 35300 | 900 | -500 | 35700
| 96 | 2027-03-06 | 19000 |  |  | 1704000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-06 | 86890 | 1145 | -300 | 87735 | 2027-03-06 | 35700 | 900 | -500 | 36100
| 97 | 2027-03-07 | 19000 |  |  | 1723000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-07 | 87735 | 1145 | -300 | 88580 | 2027-03-07 | 36100 | 900 | -500 | 36500
| 98 | 2027-03-08 | 19000 |  |  | 1742000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-08 | 88580 | 1145 | -300 | 89425 | 2027-03-08 | 36500 | 900 | -500 | 36900
| 99 | 2027-03-09 | 19000 |  |  | 1761000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-09 | 89425 | 1145 | -300 | 90270 | 2027-03-09 | 36900 | 900 | -500 | 37300
| 100 | 2027-03-10 | 19000 |  |  | 1780000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-10 | 90270 | 1145 | -300 | 91115 | 2027-03-10 | 37300 | 900 | -500 | 37700
| 101 | 2027-03-11 | 19000 |  |  | 1799000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-11 | 91115 | 1145 | -300 | 91960 | 2027-03-11 | 37700 | 900 | -500 | 38100
| 102 | 2027-03-12 | 19000 |  |  | 1818000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-12 | 91960 | 1145 | -300 | 92805 | 2027-03-12 | 38100 | 900 | -500 | 38500
| 103 | 2027-03-13 | 19000 |  |  | 1837000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-13 | 92805 | 1145 | -300 | 93650 | 2027-03-13 | 38500 | 900 | -500 | 38900
S | 104 | 2027-03-14 | 9000 |  |  | 1846000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 990 | 945 |  |  |  |  | 0 | Cleaning Plan#5 | 2027-03-14 | 93650 | 45 | -300 | 93395 | 2027-03-14 | 38900 | 900 | -500 | 39300
| 105 | 2027-03-15 | 0 |  |  | 1846000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 0 | 945 |  |  |  |  | 0 |  | 2027-03-15 | 93395 | -945 | -300 | 92150 | 2027-03-15 | 39300 | 900 | -500 | 39700
| 106 | 2027-03-16 | 19000 |  |  | 1865000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-16 | 92150 | 1145 | -300 | 92995 | 2027-03-16 | 39700 | 900 | -500 | 40100
| 107 | 2027-03-17 | 19000 |  |  | 1884000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-17 | 92995 | 1145 | -300 | 93840 | 2027-03-17 | 40100 | 900 | -500 | 40500
| 108 | 2027-03-18 | 19000 |  |  | 1903000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-18 | 93840 | 1145 | -300 | 94685 | 2027-03-18 | 40500 | 900 | -500 | 40900
| 109 | 2027-03-19 | 19000 |  |  | 1922000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-19 | 94685 | 1145 | -300 | 95530 | 2027-03-19 | 40900 | 900 | -500 | 41300
| 110 | 2027-03-20 | 19000 |  |  | 1941000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-20 | 95530 | 1145 | -300 | 96375 | 2027-03-20 | 41300 | 900 | -500 | 41700
S | 111 | 2027-03-21 | 19000 |  |  | 1960000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-21 | 96375 | 1145 | -300 | 97220 | 2027-03-21 | 41700 | 900 | -500 | 42100
| 112 | 2027-03-22 | 19000 |  |  | 1979000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-22 | 97220 | 1145 | -300 | 98065 | 2027-03-22 | 42100 | 900 | -500 | 42500
| 113 | 2027-03-23 | 19000 |  |  | 1998000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-23 | 98065 | 1145 | -300 | 98910 | 2027-03-23 | 42500 | 900 | -500 | 42900
| 114 | 2027-03-24 | 19000 |  |  | 2017000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-24 | 98910 | 1145 | -300 | 99755 | 2027-03-24 | 42900 | 900 | -500 | 43300
| 115 | 2027-03-25 | 19000 |  |  | 2036000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-25 | 99755 | 1145 | -300 | 100600 | 2027-03-25 | 43300 | 900 | -500 | 43700
| 116 | 2027-03-26 | 19000 |  |  | 2055000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-26 | 100600 | 1145 | -300 | 101445 | 2027-03-26 | 43700 | 900 | -500 | 44100
| 117 | 2027-03-27 | 19000 |  |  | 2074000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-27 | 101445 | 1145 | -300 | 102290 | 2027-03-27 | 44100 | 900 | -500 | 44500
S | 118 | 2027-03-28 | 9000 |  |  | 2083000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 990 | 945 |  |  |  |  | 0 | Cleaning Plan#6 | 2027-03-28 | 102290 | 45 | -300 | 102035 | 2027-03-28 | 44500 | 900 | -500 | 44900
| 119 | 2027-03-29 | 0 |  |  | 2083000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 0 | 945 |  |  |  |  | 0 |  | 2027-03-29 | 102035 | -945 | -300 | 100790 | 2027-03-29 | 44900 | 900 | -500 | 45300
| 120 | 2027-03-30 | 19000 |  |  | 2102000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-30 | 100790 | 1145 | -300 | 101635 | 2027-03-30 | 45300 | 900 | -500 | 45700
| 121 | 2027-03-31 | 19000 |  |  | 2121000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-03-31 | 101635 | 1145 |  | 102780 | 2027-03-31 | 45700 | 900 | -500 | 46100
| 122 | 2027-04-01 | 19000 |  |  | 2140000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-04-01 | 102780 | 1145 |  | 103925 | 2027-04-01 | 46100 | 900 | -500 | 46500
| 123 | 2027-04-02 | 19000 |  |  | 2159000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 2090 | 945 |  |  |  |  | 0 |  | 2027-04-02 | 103925 | 1145 |  | 105070 | 2027-04-02 | 46500 | 900 | -500 | 46900
| 124 | 2027-04-03 | 15000 |  |  | 2174000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 1650 | 945 |  |  |  |  | 0 |  | 2027-04-03 | 105070 | 705 |  | 105775 | 2027-04-03 | 46900 | 900 | -500 | 47300
S | 125 | 2027-04-04 | 15000 |  |  | 2189000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 1650 | 945 |  |  |  |  | 0 |  | 2027-04-04 | 105775 | 705 |  | 106480 | 2027-04-04 | 47300 | 900 | -500 | 47700
| 126 | 2027-04-05 | 15000 |  |  | 2204000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 1650 | 945 |  |  |  |  | 0 |  | 2027-04-05 | 106480 | 705 |  | 107185 | 2027-04-05 | 47700 | 900 | -500 | 48100
| 127 | 2027-04-06 | 15000 |  |  | 2219000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 1650 | 945 |  |  |  |  | 0 |  | 2027-04-06 | 107185 | 705 |  | 107890 | 2027-04-06 | 48100 | 900 | -500 | 48500
| 128 | 2027-04-07 | 15000 |  |  | 2234000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 1650 | 945 |  |  |  |  | 0 |  | 2027-04-07 | 107890 | 705 |  | 108595 | 2027-04-07 | 48500 | 900 | -500 | 48900
| 129 | 2027-04-08 | 12000 |  |  | 2246000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  |  | 1320 | 945 |  |  |  |  | 0 |  | 2027-04-08 | 108595 | 375 |  | 108970 | 2027-04-08 | 48900 | 900 | -500 | 49300
| 130 | 2027-04-09 | 12000 |  |  | 2258000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | [5 empty] | 1320 | 945 |  |  |  |  | 0 |  | 2027-04-09 | 108970 | 375 |  | 109345 | 2027-04-09 | 49300 | 900 | -500 | 49700
| 131 | 2027-04-10 | 12000 |  |  | 2270000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | [5 empty] | 1320 | 945 |  |  |  |  | 0 |  | 2027-04-10 | 109345 | 375 |  | 109720 | 2027-04-10 | 49700 | 900 | -500 | 50100
S | 132 | 2027-04-11 | 8000 |  |  | 2278000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | [5 empty] | 880 | 945 |  |  |  |  | 0 |  | 2027-04-11 | 109720 | -65 |  | 109655 | 2027-04-11 | 50100 | 900 | -500 | 50500
| 133 | 2027-04-12 | 8000 |  |  | 2286000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | [5 empty] | 880 | 945 |  |  |  |  | 0 |  | 2027-04-12 | 109655 | -65 |  | 109590 | 2027-04-12 | 50500 | 900 | -500 | 50900
| 134 | 2027-04-13 | 4000 |  |  | 2290000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | [5 empty] | 440 | 945 |  |  |  |  | 0 |  | 2027-04-13 | 109590 | -505 |  | 109085 | 2027-04-13 | 50900 | 900 | -500 | 51300
| 135 | 2027-04-14 | 4000 |  |  | 2294000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | [5 empty] | 440 | 945 |  |  |  |  | 0 | Holidays. | 2027-04-14 | 109085 | -505 |  | 108580 | 2027-04-14 | 51300 | 900 | -500 | 51700
| 136 | 2027-04-15 | 3000 |  |  | 2297000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | [5 empty] | 330 | 945 |  |  |  |  | 0 | Holidays | 2027-04-15 | 108580 | -615 |  | 107965 | 2027-04-15 | 51700 | 900 | -500 | 52100
| 137 | 2027-04-16 | 3000 |  |  | 2300000 | [15 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | [5 empty] | 330 | 945 |  |  |  | 128050 | 0 | Finished season crop 26/27 | 2027-04-16 | 107965 | -615 |  | 107350 | 2027-04-16 | 52100 | 900 | -500 | 52500 | -66500
|  | 2027-04-17 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 127105 | 0 |  | 2027-04-17 |  |  |  |  | 2027-04-17 | 52500 | 900 | -500 | 52900
S |  | 2027-04-18 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 126160 | 0 |  | 2027-04-18 |  |  |  |  | 2027-04-18 | 52900 | 900 | -500 | 53300
|  | 2027-04-19 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 125215 | 0 |  | 2027-04-19 |  |  |  |  | 2027-04-19 | 53300 | 900 | -500 | 53700
|  | 2027-04-20 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 124270 | 0 |  | 2027-04-20 |  |  |  |  | 2027-04-20 | 53700 | 900 | -500 | 54100
|  | 2027-04-21 | [16 empty] | 400 |  |  | 0 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 123325 | 0 |  | 2027-04-21 |  |  |  |  | 2027-04-21 | 54100 | 900 | -500 | 54500
|  | 2027-04-22 | [16 empty] | 400 |  |  | 0 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 122380 | 0 |  | 2027-04-22 |  |  |  |  | 2027-04-22 | 54500 | 900 | -500 | 54900
|  | 2027-04-23 | [16 empty] | 400 |  |  | 0 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 121435 | 0 |  | 2027-04-23 |  |  |  |  | 2027-04-23 | 54900 | 900 | -500 | 55300
|  | 2027-04-24 | [16 empty] | 400 |  |  | 0 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 120490 | 0 |  | 2027-04-24 |  |  |  |  | 2027-04-24 | 55300 | 900 | -500 | 55700
S |  | 2027-04-25 | [16 empty] | 400 |  |  | 0 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 119545 | 0 |  | 2027-04-25 |  |  |  |  | 2027-04-25 | 55700 | 900 | -500 | 56100
|  | 2027-04-26 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 118600 | 0 |  | 2027-04-26 |  |  |  |  | 2027-04-26 | 56100 | 900 | -500 | 56500
|  | 2027-04-27 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 117655 | 0 |  | 2027-04-27 |  |  |  |  | 2027-04-27 | 56500 | 900 | -500 | 56900
|  | 2027-04-28 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 116710 | 0 |  | 2027-04-28 |  |  |  |  | 2027-04-28 | 56900 | 900 | -500 | 57300
|  | 2027-04-29 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 115765 | 0 |  | 2027-04-29 |  |  |  |  | 2027-04-29 | 57300 | 900 | -500 | 57700
|  | 2027-04-30 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 114820 | 0 |  | 2027-04-30 |  |  |  |  | 2027-04-30 | 57700 | 900 | -500 | 58100
|  | 2027-05-01 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 113875 | 0 |  | 2027-05-01 |  |  |  |  | 2027-05-01 | 58100 | 900 | -500 | 58500
S |  | 2027-05-02 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 112930 | 0 |  | 2027-05-02 |  |  |  |  | 2027-05-02 | 58500 | 900 | -500 | 58900
|  | 2027-05-03 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 111985 | 0 |  | 2027-05-03 |  |  |  |  | 2027-05-03 | 58900 | 900 | -500 | 59300
|  | 2027-05-04 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 111040 | 0 |  | 2027-05-04 |  |  |  |  | 2027-05-04 | 59300 | 900 | -500 | 59700
|  | 2027-05-05 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 110095 | 0 |  | 2027-05-05 |  |  |  |  | 2027-05-05 | 59700 | 900 | -500 | 60100
|  | 2027-05-06 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 109150 | 0 |  | 2027-05-06 |  |  |  |  | 2027-05-06 | 60100 | 900 | -500 | 60500
|  | 2027-05-07 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 108205 | 0 |  | 2027-05-07 |  |  |  |  | 2027-05-07 | 60500 | 900 | -500 | 60900
|  | 2027-05-08 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 107260 | 0 |  | 2027-05-08 |  |  |  |  | 2027-05-08 | 60900 | 900 | -500 | 61300
S |  | 2027-05-09 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 106315 | 0 |  | 2027-05-09 |  |  |  |  | 2027-05-09 | 61300 | 900 | -500 | 61700
|  | 2027-05-10 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 105370 | 0 |  | 2027-05-10 |  |  |  |  | 2027-05-10 | 61700 | 900 | -500 | 62100
|  | 2027-05-11 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 104425 | 0 |  | 2027-05-11 |  |  |  |  | 2027-05-11 | 62100 | 900 | -500 | 62500
|  | 2027-05-12 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 103480 | 0 |  | 2027-05-12 |  |  |  |  | 2027-05-12 | 62500 | 900 | -500 | 62900
|  | 2027-05-13 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 102535 | 0 |  | 2027-05-13 |  |  |  |  | 2027-05-13 | 62900 | 900 | -500 | 63300
|  | 2027-05-14 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 101590 | 0 |  | 2027-05-14 |  |  |  |  | 2027-05-14 | 63300 | 900 | -500 | 63700
|  | 2027-05-15 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 100645 | 0 |  | 2027-05-15 |  |  |  |  | 2027-05-15 | 63700 | 900 | -500 | 64100
S |  | 2027-05-16 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 99700 | 0 |  | 2027-05-16 |  |  |  |  | 2027-05-16 | 64100 | 900 | -500 | 64500
|  | 2027-05-17 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 98755 | 0 |  | 2027-05-17 |  |  |  |  | 2027-05-17 | 64500 | 900 | -500 | 64900
|  | 2027-05-18 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 97810 | 0 |  | 2027-05-18 |  |  |  |  | 2027-05-18 | 64900 | 900 | -500 | 65300
|  | 2027-05-19 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 96865 | 0 |  | 2027-05-19 |  |  |  |  | 2027-05-19 | 65300 | 900 | -500 | 65700
|  | 2027-05-20 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 95920 | 0 |  | 2027-05-20 |  |  |  |  | 2027-05-20 | 65700 | 900 | -500 | 66100
|  | 2027-05-21 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 94975 | 0 |  | 2027-05-21 |  |  |  |  | 2027-05-21 | 66100 | 900 | -500 | 66500
|  | 2027-05-22 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 94030 | 0 |  | 2027-05-22 |  |  |  |  | 2027-05-22 | 66500 | 900 | -500 | 66900
S |  | 2027-05-23 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 93085 | 0 |  | 2027-05-23 |  |  |  |  | 2027-05-23 | 66900 | 900 | -500 | 67300
|  | 2027-05-24 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 92140 | 0 |  | 2027-05-24 |  |  |  |  | 2027-05-24 | 67300 | 900 | -500 | 67700
|  | 2027-05-25 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 91195 | 0 |  | 2027-05-25 |  |  |  |  | 2027-05-25 | 67700 | 900 | -500 | 68100
|  | 2027-05-26 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 90250 | 0 |  | 2027-05-26 |  |  |  |  | 2027-05-26 | 68100 | 900 | -500 | 68500
|  | 2027-05-27 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 89305 | 0 |  | 2027-05-27 |  |  |  |  | 2027-05-27 | 68500 | 900 | -500 | 68900
|  | 2027-05-28 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 88360 | 0 |  | 2027-05-28 |  |  |  |  | 2027-05-28 | 68900 | 900 | -500 | 69300
|  | 2027-05-29 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 87415 | 0 |  | 2027-05-29 |  |  |  |  | 2027-05-29 | 69300 | 900 | -500 | 69700
S |  | 2027-05-30 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 86470 | 0 |  | 2027-05-30 |  |  |  |  | 2027-05-30 | 69700 | 900 | -500 | 70100
|  | 2027-05-31 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 85525 | 0 |  | 2027-05-31 |  |  |  |  | 2027-05-31 | 70100 | 900 | -500 | 70500
|  | 2027-06-01 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 84580 | 0 |  | 2027-06-01 |  |  |  |  | 2027-06-01 | 70500 | 900 | -500 | 70900
|  | 2027-06-02 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 83635 | 0 |  | 2027-06-02 |  |  |  |  | 2027-06-02 | 70900 | 900 | -500 | 71300
|  | 2027-06-03 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 82690 | 0 |  | 2027-06-03 |  |  |  |  | 2027-06-03 | 71300 | 900 | -500 | 71700
|  | 2027-06-04 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 81745 | 0 |  | 2027-06-04 |  |  |  |  | 2027-06-04 | 71700 | 900 | -500 | 72100
|  | 2027-06-05 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 80800 | 0 |  | 2027-06-05 |  |  |  |  | 2027-06-05 | 72100 | 900 | -500 | 72500
S |  | 2027-06-06 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 79855 | 0 |  | 2027-06-06 |  |  |  |  | 2027-06-06 | 72500 | 900 | -500 | 72900
|  | 2027-06-07 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 78910 | 0 |  | 2027-06-07 |  |  |  |  | 2027-06-07 | 72900 | 900 | -500 | 73300
|  | 2027-06-08 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 77965 | 0 |  | 2027-06-08 |  |  |  |  | 2027-06-08 | 73300 | 900 | -500 | 73700
|  | 2027-06-09 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 77020 | 0 |  | 2027-06-09 |  |  |  |  | 2027-06-09 | 73700 | 900 | -500 | 74100
|  | 2027-06-10 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 76075 | 0 |  | 2027-06-10 |  |  |  |  | 2027-06-10 | 74100 | 900 | -500 | 74500
|  | 2027-06-11 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 75130 | 0 |  | 2027-06-11 |  |  |  |  | 2027-06-11 | 74500 | 900 | -500 | 74900
|  | 2027-06-12 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 74185 | 0 |  | 2027-06-12 |  |  |  |  | 2027-06-12 | 74900 | 900 | -500 | 75300
S |  | 2027-06-13 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 73240 | 0 |  | 2027-06-13 |  |  |  |  | 2027-06-13 | 75300 | 900 | -500 | 75700
|  | 2027-06-14 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 72295 | 0 |  | 2027-06-14 |  |  |  |  | 2027-06-14 | 75700 | 900 | -500 | 76100
|  | 2027-06-15 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 71350 | 0 |  | 2027-06-15 |  |  |  |  | 2027-06-15 | 76100 | 900 | -500 | 76500
|  | 2027-06-16 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 70405 | 0 |  | 2027-06-16 |  |  |  |  | 2027-06-16 | 76500 | 900 | -500 | 76900
|  | 2027-06-17 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 69460 | 0 |  | 2027-06-17 |  |  |  |  | 2027-06-17 | 76900 | 900 | -500 | 77300
|  | 2027-06-18 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 68515 | 0 |  | 2027-06-18 |  |  |  |  | 2027-06-18 | 77300 | 900 | -500 | 77700
|  | 2027-06-19 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 67570 | 0 |  | 2027-06-19 |  |  |  |  | 2027-06-19 | 77700 | 900 | -500 | 78100
S |  | 2027-06-20 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 66625 | 0 |  | 2027-06-20 |  |  |  |  | 2027-06-20 | 78100 | 900 | -500 | 78500
|  | 2027-06-21 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 65680 | 0 |  | 2027-06-21 |  |  |  |  | 2027-06-21 | 78500 | 900 | -500 | 78900
|  | 2027-06-22 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 64735 | 0 |  | 2027-06-22 |  |  |  |  | 2027-06-22 | 78900 | 900 | -500 | 79300
|  | 2027-06-23 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 63790 | 0 |  | 2027-06-23 |  |  |  |  | 2027-06-23 | 79300 | 900 | -500 | 79700
|  | 2027-06-24 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 62845 | 0 |  | 2027-06-24 |  |  |  |  | 2027-06-24 | 79700 | 900 | -500 | 80100
|  | 2027-06-25 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 61900 | 0 |  | 2027-06-25 |  |  |  |  | 2027-06-25 | 80100 | 900 | -500 | 80500
|  | 2027-06-26 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 60955 | 0 |  | 2027-06-26 |  |  |  |  | 2027-06-26 | 80500 | 900 | -500 | 80900
S |  | 2027-06-27 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 60010 | 0 |  | 2027-06-27 |  |  |  |  | 2027-06-27 | 80900 | 900 | -500 | 81300
|  | 2027-06-28 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 59065 | 0 |  | 2027-06-28 |  |  |  |  | 2027-06-28 | 81300 | 900 | -500 | 81700
|  | 2027-06-29 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 58120 | 0 |  | 2027-06-29 |  |  |  |  | 2027-06-29 | 81700 | 900 | -500 | 82100
|  | 2027-06-30 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 57175 | 0 |  | 2027-06-30 |  |  |  |  | 2027-06-30 | 82100 | 900 | -500 | 82500
|  | 2027-07-01 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 56230 | 0 |  | 2027-07-01 |  |  |  |  | 2027-07-01 | 82500 | 900 | -500 | 82900
|  | 2027-07-02 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 55285 | 0 |  | 2027-07-02 |  |  |  |  | 2027-07-02 | 82900 | 900 | -500 | 83300
|  | 2027-07-03 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 54340 | 0 |  | 2027-07-03 |  |  |  |  | 2027-07-03 | 83300 | 900 | -500 | 83700
S |  | 2027-07-04 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 53395 | 0 |  | 2027-07-04 |  |  |  |  | 2027-07-04 | 83700 | 900 | -500 | 84100
|  | 2027-07-05 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 52450 | 0 |  | 2027-07-05 |  |  |  |  | 2027-07-05 | 84100 | 900 | -500 | 84500
|  | 2027-07-06 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 51505 | 0 |  | 2027-07-06 |  |  |  |  | 2027-07-06 | 84500 | 900 | -500 | 84900
|  | 2027-07-07 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 50560 | 0 |  | 2027-07-07 |  |  |  |  | 2027-07-07 | 84900 | 900 | -500 | 85300
|  | 2027-07-08 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 49615 | 0 |  | 2027-07-08 |  |  |  |  | 2027-07-08 | 85300 | 900 | -500 | 85700
|  | 2027-07-09 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 48670 | 0 |  | 2027-07-09 |  |  |  |  | 2027-07-09 | 85700 | 900 | -500 | 86100
|  | 2027-07-10 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 47725 | 0 |  | 2027-07-10 |  |  |  |  | 2027-07-10 | 86100 | 900 | -500 | 86500
S |  | 2027-07-11 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 46780 | 0 |  | 2027-07-11 |  |  |  |  | 2027-07-11 | 86500 | 900 | -500 | 86900
|  | 2027-07-12 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 45835 | 0 |  | 2027-07-12 |  |  |  |  | 2027-07-12 | 86900 | 900 | -500 | 87300
|  | 2027-07-13 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 44890 | 0 |  | 2027-07-13 |  |  |  |  | 2027-07-13 | 87300 | 900 | -500 | 87700
|  | 2027-07-14 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 43945 | 0 |  | 2027-07-14 |  |  |  |  | 2027-07-14 | 87700 | 900 | -500 | 88100
|  | 2027-07-15 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 43000 | 0 |  | 2027-07-15 |  |  |  |  | 2027-07-15 | 88100 | 900 | -500 | 88500
|  | 2027-07-16 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 42055 | 0 |  | 2027-07-16 |  |  |  |  | 2027-07-16 | 88500 | 900 | -500 | 88900
|  | 2027-07-17 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 41110 | 0 |  | 2027-07-17 |  |  |  |  | 2027-07-17 | 88900 | 900 | -500 | 89300
S |  | 2027-07-18 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 40165 | 0 |  | 2027-07-18 |  |  |  |  | 2027-07-18 | 89300 | 900 | -500 | 89700
|  | 2027-07-19 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 39220 | 0 |  | 2027-07-19 |  |  |  |  | 2027-07-19 | 89700 | 900 | -500 | 90100
|  | 2027-07-20 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 38275 | 0 |  | 2027-07-20 |  |  |  |  | 2027-07-20 | 90100 | 900 | -500 | 90500
|  | 2027-07-21 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 37330 | 0 |  | 2027-07-21 |  |  |  |  | 2027-07-21 | 90500 | 900 | -500 | 90900
|  | 2027-07-22 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 | 0 |  |  |  | 945 | [5 empty] | 36385 | 0 |  | 2027-07-22 |  |  |  |  | 2027-07-22 | 90900 | 900 | -500 | 91300
|  | 2027-07-23 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 35440 | 0 |  | 2027-07-23 |  |  |  |  | 2027-07-23 | 91300 | 900 | -500 | 91700
|  | 2027-07-24 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 34495 | 0 |  | 2027-07-24 |  |  |  |  | 2027-07-24 | 91700 | 900 | -500 | 92100
|  | 2027-07-25 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 33550 | 0 |  | 2027-07-25 |  |  |  |  | 2027-07-25 | 92100 | 900 | -500 | 92500
|  | 2027-07-26 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 32605 | 0 |  | 2027-07-26 |  |  |  |  | 2027-07-26 | 92500 | 900 | -500 | 92900
|  | 2027-07-27 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 31660 | 0 |  | 2027-07-27 |  |  |  |  | 2027-07-27 | 92900 | 900 | -500 | 93300
|  | 2027-07-28 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 30715 | 0 |  | 2027-07-28 |  |  |  |  | 2027-07-28 | 93300 | 900 | -500 | 93700
|  | 2027-07-29 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 29770 | 0 |  | 2027-07-29 |  |  |  |  | 2027-07-29 | 93700 | 900 | -500 | 94100
|  | 2027-07-30 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 28825 | 0 |  | 2027-07-30 |  |  |  |  | 2027-07-30 | 94100 | 900 | -500 | 94500
|  | 2027-07-31 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 27880 | 0 |  | 2027-07-31 |  |  |  |  | 2027-07-31 | 94500 | 900 | -500 | 94900
|  | 2027-08-01 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 26935 | 0 |  | 2027-08-01 |  |  |  |  | 2027-08-01 | 94900 | 900 | -500 | 95300
|  | 2027-08-02 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 25990 | 0 |  | 2027-08-02 |  |  |  |  | 2027-08-02 | 95300 | 900 | -500 | 95700
|  | 2027-08-03 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 25045 | 0 |  | 2027-08-03 |  |  |  |  | 2027-08-03 | 95700 | 900 | -500 | 96100
|  | 2027-08-04 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 24100 | 0 |  | 2027-08-04 |  |  |  |  | 2027-08-04 | 96100 | 900 | -500 | 96500
|  | 2027-08-05 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 23155 | 0 |  | 2027-08-05 |  |  |  |  | 2027-08-05 | 96500 | 900 | -500 | 96900
|  | 2027-08-06 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 22210 | 0 |  | 2027-08-06 |  |  |  |  | 2027-08-06 | 96900 | 900 | -500 | 97300
|  | 2027-08-07 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 21265 | 0 |  | 2027-08-07 |  |  |  |  | 2027-08-07 | 97300 | 900 | -500 | 97700
|  | 2027-08-08 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 20320 | 0 |  | 2027-08-08 |  |  |  |  | 2027-08-08 | 97700 | 900 | -500 | 98100
|  | 2027-08-09 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 19375 | 0 |  | 2027-08-09 |  |  |  |  | 2027-08-09 | 98100 | 900 | -500 | 98500
|  | 2027-08-10 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 18430 | 0 |  | 2027-08-10 |  |  |  |  | 2027-08-10 | 98500 | 900 | -500 | 98900
|  | 2027-08-11 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 17485 | 0 |  | 2027-08-11 |  |  |  |  | 2027-08-11 | 98900 | 900 | -500 | 99300
|  | 2027-08-12 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 16540 | 0 |  | 2027-08-12 |  |  |  |  | 2027-08-12 | 99300 | 900 | -500 | 99700
|  | 2027-08-13 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 15595 | 0 |  | 2027-08-13 |  |  |  |  | 2027-08-13 | 99700 | 900 | -500 | 100100
|  | 2027-08-14 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 14650 | 0 |  | 2027-08-14 |  |  |  |  | 2027-08-14 | 100100 | 900 | -500 | 100500
|  | 2027-08-15 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 13705 | 0 |  | 2027-08-15 |  |  |  |  | 2027-08-15 | 100500 | 900 | -500 | 100900
|  | 2027-08-16 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 12760 | 0 |  | 2027-08-16 |  |  |  |  | 2027-08-16 | 100900 | 900 | -500 | 101300
|  | 2027-08-17 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 11815 | 0 |  | 2027-08-17 |  |  |  |  | 2027-08-17 | 101300 | 900 | -500 | 101700
|  | 2027-08-18 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 10870 | 0 |  | 2027-08-18 |  |  |  |  | 2027-08-18 | 101700 | 900 | -500 | 102100
|  | 2027-08-19 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 9925 | 0 |  | 2027-08-19 |  |  |  |  | 2027-08-19 | 102100 | 900 | -500 | 102500
|  | 2027-08-20 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 8980 | 0 |  | 2027-08-20 |  |  |  |  | 2027-08-20 | 102500 | 900 | -500 | 102900
|  | 2027-08-21 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 8035 | 0 |  | 2027-08-21 |  |  |  |  | 2027-08-21 | 102900 | 900 | -500 | 103300
|  | 2027-08-22 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 7090 | 0 |  | 2027-08-22 |  |  |  |  | 2027-08-22 | 103300 | 900 | -500 | 103700
|  | 2027-08-23 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 6145 | 0 |  | 2027-08-23 |  |  |  |  | 2027-08-23 | 103700 | 900 | -500 | 104100
|  | 2027-08-24 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 5200 | 0 |  | 2027-08-24 |  |  |  |  | 2027-08-24 | 104100 | 900 | -500 | 104500
|  | 2027-08-25 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 4255 | 0 |  | 2027-08-25 |  |  |  |  | 2027-08-25 | 104500 | 900 | -500 | 104900
|  | 2027-08-26 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 3310 | 0 |  | 2027-08-26 |  |  |  |  | 2027-08-26 | 104900 | 900 | -500 | 105300
|  | 2027-08-27 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 2365 | 0 |  | 2027-08-27 |  |  |  |  | 2027-08-27 | 105300 | 900 | -500 | 105700
|  | 2027-08-28 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 1420 | 0 |  | 2027-08-28 |  |  |  |  | 2027-08-28 | 105700 | 900 | -500 | 106100
|  | 2027-08-29 | [19 empty] | 400 |  | 1600 | [12 empty] | 500 | [15 empty] | 900 | 0 |  |  |  |  | 945 | [5 empty] | 475 | 0 |  | 2027-08-29 |  |  |  |  | 2027-08-29 | 106100 | 900 | -500 | 106500
|  | 2027-08-30 | [19 empty] | 400 |  | 1600 | [28 empty] | 450 | 0 |  |  |  |  | 472.5 | [5 empty] | 2.5 | 0 |  | 2027-08-30 |  |  |  |  | 2027-08-30 | 106500 | 450 | -500 | 106450
|  | 2027-08-31 | [19 empty] | 400 |  | 1200 | [12 empty] | 0 | [15 empty] | 400 | 0 | [11 empty] | 0 |  | 2027-08-31 |  |  |  |  | 2027-08-31 | 106450 | 400 | -500 | 106350
|  | 2027-09-01 | [19 empty] | 400 |  | 800 | [12 empty] | 0 | [15 empty] | 400 | 0 | [11 empty] | 0 |  | 2027-09-01 |  |  |  |  | 2027-09-01 | 106350 | 400 | -500 | 106250
|  | 2027-09-02 | [19 empty] | 400 |  | 400 | [12 empty] | 0 | [15 empty] | 400 | 0 | [11 empty] | 0 | End of The Remelt season'27 | 2027-09-02 |  |  |  |  | 2027-09-02 | 106250 | 400 | -500 | 106150
|  | 2027-09-03 | [63 empty] | 0
|  | 2027-09-04 | [63 empty] | 0
|  | 2027-09-05 | [63 empty] | 0
|  | 2027-09-06 | [63 empty] | 0
|  | 2027-09-07 | [63 empty] | 0
|  | 2027-09-08 | [63 empty] | 0
|  | 2027-09-09 | [63 empty] | 0
|  | 2027-09-10 | [63 empty] | 0
|  | 2027-09-11 | [63 empty] | 0
|  | 2027-09-12 | [63 empty] | 0
|  | 2027-09-13 | [63 empty] | 0
|  | 2027-09-14 | [63 empty] | 0
|  | 2027-09-15 | [63 empty] | 0
|  | 2027-09-16 | [63 empty] | 0
|  | 2027-09-17 | [63 empty] | 0
|  | 2027-09-18 | [63 empty] | 0
|  | 2027-09-19 | [63 empty] | 0
|  | 2027-09-20 | [63 empty] | 0
|  | 2027-09-21 | [63 empty] | 0
|  | 2027-09-22 | [63 empty] | 0
|  | 2027-09-23 | [63 empty] | 0
|  | 2027-09-24 | [63 empty] | 0
|  | 2027-09-25 | [63 empty] | 0
|  | 2027-09-26 | [63 empty] | 0
|  | 2027-09-27 | [63 empty] | 0
|  | 2027-09-28 | [63 empty] | 0
|  | 2027-09-29 | [63 empty] | 0
|  | 2027-09-30 | [63 empty] | 0
[53 empty] | 0 | 0 | [11 empty] | 0
[53 empty] | 0 | 0 | [11 empty] | 0
|  | SUM | 2300000 | [15 empty] | 2000 | 0 | 0 | 106700 | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 133400 | 0 | [13 empty] | 0 | 242100 | 0 | 0 | 0 | 0 | 0 | 128047.5 | 253000 | 124950 | 0 | 0 | 0
Formulas:
Raw Sugar in SILO (ton) = [Refined & White Sugar in SILO (ton)]
Raw Sugar in SILO (ton) = [Raw Sugar in SILO (ton), row above]+1
Refined & White Sugar in SILO (ton) = [Date]
Refined & White Sugar in SILO (ton) = [Refined & White Sugar in SILO (ton), row above]+1
Date = [Date, row above]+1
Note on CG6: Corrected capacity: WH1 22,000 t + WH3 47,000 t = 69,000 t (revised refined-sugar warehouse plan). Was 20,000+50,000.
Note on Y24: Fill:RCon.Silo400t/d
Note on CG294: Tracker extended to end of remelt season (02-Sep-2027); previously stopped 25-Aug-2027 and missed the last 8 production days.
Note on BQ325: Tingly: 255.106 Tons Raw to Silo on 05-06 April 2026 108443.407T+255.106T(ចូលឃ្លាំងវិញ)